PM
PITCH
EXT
JUSTIFICATION
PRODUCT
ASSUMPTIONS
ASSUMPTIONS
ASSUMPTIONS
ASSUMPTIONS
RISKS
STAKEHOLDERS
Search for libraries to use;
Problems with organizing private chat.
The project will be
released on Friday 13,
2019;
The Team Manager will
talk to others and make
meetings with members
of his team.
It manages public messages and the graphic part is complete and functional.
Consultancy on project management;
Absence of a group member.
Unsatisfactory graphics;
Failure to mange private messages;
Failure to manage public messages.
REQUIREMENTS
SMART
OBJECTIVE
It must have graphics that are pleasing to the customer;
It must efficiently manage the exchange of packets which must comply with the initially established requirements;
Knowing how to manage private and public messages.
Create a chat application,
which manages the exchange
of private and public messages
through a correct exchange of
packages.
TEAM
TIMELINE
DELIVERABLES
Marchi Enrico is the Team Manager and SoftwareDeveloper;
Bulai Matteo Software Developer;
Gaole Elia Graphic Designer;
Emiliani Jennifer Graphic Designer;
Grippi Giulio Graphic Designer.
1-Start 31 October 2019.
2-Implement the registration
 method 25 November 2019.
3-End the Login / Logout
methods December 4, 2019.
4-Implement the
ControlMessages class
December 6, 2019.
5-Conclusion 12 December
2019.
1-Meeting of group
 members.
2-Implementation strategy.
3-Test the operation of the
application.
4-Presentation of the
application.
BENEFITS
Improve the relationship with other developers;
Improve cooperation in the group;
Self-managing compartment; Discovered new java libraries.
COSTS
No costs were applied to this project.
CONTRAINTS
Internal IT staff will not support the new application;
At the end of the time available you cannot fail to commit your work;
Do not marge the code without the consent of the other group members.
Project Model Canvas
José Finocchio Junior